## Sheet1
|  | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F | Sa | Su | M | Tu | W | Th | F
No. | Task/Deliverable | 2021-04-04 | 2021-04-05 | 2021-04-06 | 2021-04-07 | 2021-04-08 | 2021-04-09 | 2021-04-10 | 2021-04-11 | 2021-04-12 | 2021-04-13 | 2021-04-14 | 2021-04-15 | 2021-04-16 | 2021-04-17 | 2021-04-18 | 2021-04-19 | 2021-04-20 | 2021-04-21 | 2021-04-22 | 2021-04-23 | 2021-04-24 | 2021-04-25 | 2021-04-26 | 2021-04-27 | 2021-04-28 | 2021-04-29 | 2021-04-30 | 2021-05-01 | 2021-05-02 | 2021-05-03 | 2021-05-04 | 2021-05-05 | 2021-05-06 | 2021-05-07
0 | Deliverable Phase 0: Project Proposal | 2021-04-13: ⓪
0.1 | Form project group | bar: 2021-04-04 to 2021-04-05
0.2 | Determine objective | bar: 2021-04-04 to 2021-04-06
0.3 | Project review/description | bar: 2021-04-04 to 2021-04-07
0.4 | Project kick-off meeting | bar: 2021-04-08
0.5 | Abstract | bar: 2021-04-09 to 2021-04-10
0.6 | Data description | bar: 2021-04-09 to 2021-04-12
0.7 | Algorithms (baseline/additional) & metrics | bar: 2021-04-09 to 2021-04-12
0.8 | Pipelines (baseline/additional) | bar: 2021-04-09 to 2021-04-12
0.9 | Overall proposal layout | bar: 2021-04-11 to 2021-04-12
1 | Deliverable Phase 1: Baseline Model & Report (application data) | 2021-04-20: ①
1.1 | Load data | bar: 2021-04-09 to 2021-04-13
1.2 | Exploratory data analysis | bar: 2021-04-09 to 2021-04-16
1.3 | Test design (models & metrics) | bar: 2021-04-11 to 2021-04-13
1.4 | Pipeline (baseline) | bar: 2021-04-12 to 2021-04-16
1.4.1 | Feature engineering (baseline) | bar: 2021-04-12 to 2021-04-16
1.4.2 | Models (baseline) | bar: 2021-04-12 to 2021-04-16
1.4.3 | Hyperparameter tuning (baseline) | bar: 2021-04-12 to 2021-04-16
1.5 | Evaluation & results (baseline) | bar: 2021-04-17 to 2021-04-18
1.6 | Kaggle submission | bar: 2021-04-19
1.7 | Brief report | bar: 2021-04-15 to 2021-04-19
2 | Deliverable Phase 2: Ensemble Model & Report (application, bureau, previous application, payment history data) | 2021-04-27: ②
2.1 | Load data (bureau, previous application data, payment history data) | bar: 2021-04-14 to 2021-04-20
2.2 | Exploratory data analysis (bureau, previous application data, payment history data) | bar: 2021-04-14 to 2021-04-23
2.3 | Test design (models & metrics) | bar: 2021-04-16 to 2021-04-20
2.4 | Pipeline (ensemble) | bar: 2021-04-19 to 2021-04-23
2.4.1 | Feature engineering (ensemble) | bar: 2021-04-19 to 2021-04-23
2.4.2 | Models (ensemble) | bar: 2021-04-19 to 2021-04-23
2.4.3 | Hyperparameter tuning (ensemble) | bar: 2021-04-19 to 2021-04-23
2.5 | Evaluation & results (ensemble) | bar: 2021-04-24 to 2021-04-25
2.6 | Kaggle submission | bar: 2021-04-26
2.7 | Brief report | bar: 2021-04-22 to 2021-04-26
3 | Deliverable Final Submission: Neural Network Model & Report (application, bureau, previous application, payment history data) | 2021-05-04: ③
3.1 | Test design (models & metrics) | bar: 2021-04-24 to 2021-04-29
3.2 | Pipeline (DNN) | bar: 2021-04-25 to 2021-04-30
3.2.1 | Feature engineering (DNN) | bar: 2021-04-25 to 2021-04-30
3.2.2 | Models (DNN) | bar: 2021-04-25 to 2021-04-30
3.3 | Evaluation & results (DNN) | bar: 2021-04-29 to 2021-05-01
3.4 | Kaggle submission | bar: 2021-05-01 to 2021-05-02
3.5 | Final report | bar: 2021-04-28 to 2021-05-03
3.6 | Final presentation | bar: 2021-05-01 to 2021-05-03
3.6.1 | Prepare presentation | bar: 2021-05-01 to 2021-05-03
3.6.2 | Record presentation | bar: 2021-05-03
3.6.3 | Post presentation | bar: 2021-05-03
4 | Feedback | bar: 2021-05-04 to 2021-05-07